## Start
Contractor Estimate-to-Actual Pack
WORKED EXAMPLE (fictional job, fictional numbers)
Your inputs
Job name | Garage outlet upgrade (fictional)
Base hourly wage ($) | 30
Labor burden % of wages (employer payroll taxes, workers comp, benefits, paid time off, training, tools). Use YOUR number. | 40%
Fully burdened hourly rate
Pricing method (Markup or Margin) | Markup
Markup or margin % | 50%
Overhead allowance % of price (office, admin, general liability and other business-wide costs NOT already in your burden %). Use YOUR number. | 10%
How to use (about 5 minutes a week):
1. Fill the yellow cells above once. Your burden % is the number most people leave out. $30/hr wage at 40% burden costs $42/hr.
2. Estimate tab: one row per cost code. Labor hours use the burdened rate automatically.
3. Freeze the estimate when the customer signs. Never edit it after that. Copy the totals into Tracker (they carry over automatically).
4. Change Orders tab: log every approved scope change with its own price and cost. Extras Tab: log work done WITHOUT a signed change order.
5. Tracker tab: update actual, open commitments (signed or ordered, not yet billed to you) and forecast to complete every week, not at closeout.
6. Weekly tab: the 5-question Sunday check. Closeout tab: fill when the job ends.
Terms:
Original budget: your direct-cost estimate by cost code, frozen when the contract is signed. Revised budget: original plus approved change orders.
Change order: a written, approved change to the scope and price of the contract. Work done without one goes on the Extras tab.
Actual: costs incurred on the job to date, including vendor and sub bills you have received even if unpaid, plus labor at the burdened rate. Open commitments: signed subcontracts and purchase orders for the part not yet billed to you.
Forecast to complete: what you still expect to spend on work not yet bought or committed. Projected final cost = actual + open commitments + forecast to complete.
Variance = revised budget minus projected final cost. Negative (red) means over budget.
Markup = (price - cost) / cost. Margin = (price - cost) / price. A 20% markup is only a 16.7% margin.
Direct job costs: labor at the burdened rate, materials, subcontractors, equipment, permits, dump fees and job supplies. Overhead: business-wide costs not tied to one job (office, admin, general liability, owner pay).
Burden vs overhead: put a cost in one or the other, never both. Workers comp usually sits in burden; general liability usually in overhead.
Gross profit = price minus direct job costs. Profit after overhead allowance also subtracts your overhead % of price. Neither is tax profit or take-home cash.
Limits: a management worksheet, not tax, GAAP or accounting advice. Cost definitions follow public construction-accounting references (Procore, Deltek, Foundation Software, CPA-firm and job-costing publications). No macros, no external links.

## Estimate
Estimate by cost code (freeze at signing)
Cost code | Description | Labor hours | Burdened rate ($/hr) | Labor $ | Materials $ | Subs $ | Equipment / other $ | Total direct cost $
01 Prep | Prep and protection | 4 |  |  | 132 | 0 | 0
02 Framing | Framing and rough-in | 8 |  |  | 264 | 0 | 0
03 Electrical | Electrical (licensed sub) | 5 |  |  | 0 | 190 | 0
04 Finish | Finish and paint | 6 |  |  | 248 | 0 | 0
05 Cleanup | Cleanup and haul-off | 2 |  |  | 0 | 0 | 116
Total direct cost
Pricing method
Price before change orders
Equivalent margin %
Equivalent markup %
Price is a starting point. Round it, check your market, and make sure the margin still covers overhead.

## ChangeOrders
Change orders (approved scope changes only)
CO # | Cost code | What changed | Why (customer request / hidden condition) | Price to customer $ | Cost budget $ | Approved? (Y/N) | Billed? (Y/N)
CO-1 | 03 Electrical | Two extra outlets | Customer request | 300 | 180 | Y | Y
Total approved
Cost code must match a code on the Estimate tab exactly. Only rows marked Y count toward the revised budget.

## Extras
Absorbed extras (work done with NO signed change order)
Every 'while you're here' favor is a real cost. If it happens, log it here and decide: bill it or eat it on purpose.
Date | Cost code | What was done | Hours | Burdened labor $ | Materials $ | Total cost $ | Decision (Bill it / Eat it)
Total absorbed

## Tracker
Job tracker: one row per cost code. Update weekly.
Cost code | Description | Original budget | Approved change orders | Revised budget | Actual to date | (of actual) spent on change-order work | Open commitments | Forecast to complete | Projected final cost | Variance (revised budget - projected) | Flag
[5 empty] | 350 | 0 | 0 | 0
[5 empty] | 650 | 0 | 0 | 0
[5 empty] | 610 | 210 | 0 | 0
[5 empty] | 550 | 0 | 0 | 0
[5 empty] | 200 | 0 | 0 | 0
TOTAL
WATCH = less than 10% of the revised budget left after projecting to the end. Enter the actual on change-order work in column G so closeout can split scope drift from change drift.

## Weekly
Weekly 5-minute check (Sunday admin). Do it every week the job is open.
Week of | 1. All receipts coded to a job and cost code? | 2. All crew hours logged at the burdened rate? | 3. Open commitments (POs, subs) entered? | 4. Forecast to complete updated? | 5. Any extra done without a change order? | Notes / decision
Wk 1 | Y | Y | Y | Y | N | On track
Wk 2 | Y | Y | Y | Y | N | Outlets: signed CO-1 before work

## Closeout
Closeout: estimated vs actual
Cost code | Original budget | Revised budget | Actual | Original-scope drift | Change-order drift
TOTAL
Job result
Original price
Approved change-order price
Total price
Total actual direct cost
Gross profit (price - direct cost)
Overhead allowance (% of price from Start)
Profit after overhead allowance (estimate). Not tax profit or take-home cash.
Absorbed extras logged on Extras tab (cost already in actual only if you also coded it)
Total overrun vs original budget (actual - original)
of which: extra scope you were paid for (approved COs)
of which: original-scope drift
of which: change-order drift
Three lessons for the next estimate:
Prep, framing and finish were each $50 over: add a contingency line to those three codes next time.
Electrical extra work cost $210 against a $180 change budget: price hidden-condition CO work with a 15% buffer.
No extras absorbed: keep signing the CO before starting.